## Cover
Dodol
User Acceptance Testing Plan
Version | 1.0
App | Dodol Recipe Keeper
Platforms | iOS (native app) · Web (browser)
Date | 7 April 2026
How to use this document
Work through each section tab in order. For each test, do the action described, then enter
Pass ✅ or Fail ❌ in the Result column and add any observations in the Notes column.
[iOS] = test on the iPhone app only
[Web] = test on a browser (Chrome or Safari recommended)
[Both] = test on both platforms
Testers should create their own account from scratch to get a clean experience.
Complete the Feedback Summary tab when you have finished all sections.
Sections
1 · Authentication
2 · Recipe Library
3 · Recipe Capture
4 · Recipe Detail
5 · Sous Chef
6 · iOS Share Extension
7 · Account Page
8 · Paywall & Subscription
9 · Navigation Consistency
10 · Performance & Stability
11 · Error States
Feedback Summary

## 1 · Authentication
1 · Authentication
1.1 Sign Up
# | Action | Expected Result | Platform | Result | Notes
1.1.1 | Open the app for the first time | Sign-in screen appears | Both
1.1.2 | Tap "Create account" and enter a new email + password | Account created, redirected to the recipe library | Both
1.1.3 | Sign out (Account → Sign out), then sign back in with the same credentials | Successfully signed back in | Both
1.2 Sign In / Sign Out
# | Action | Expected Result | Platform | Result | Notes
1.2.1 | Sign in with a wrong password | Error message shown, not signed in | Both
1.2.2 | Sign in with a wrong email | Error message shown, not signed in | Both
1.2.3 | Sign out from the Account page | Redirected to sign-in screen | Both

## 2 · Recipe Library
2 · Recipe Library
# | Action | Expected Result | Platform | Result | Notes
2.1 | Open the app after signing in | Recipe library loads; shows "No recipes yet" if empty | Both
2.2 | Scroll through a library with several recipes | Cards load and scroll smoothly | Both
2.3 | Tap a recipe card | Opens the recipe detail page | Both
2.4 | Tap "Capture a Recipe" / the + button | Opens the Capture page | Both
2.5 | Tap the account icon / "Account" | Opens the Account page | Both

## 3 · Recipe Capture
3 · Recipe Capture
3.1 Narrate
# | Action | Expected Result | Platform | Result | Notes
3.1.1 | Open Capture → select "Narrate" tab | Voice capture UI appears with a microphone button | Both
3.1.2 | Tap the mic and describe a simple recipe out loud (e.g. scrambled eggs) | Speech is transcribed into the text area in real time | Both
3.1.3 | Tap "Generate Recipe" | Animated loading screen appears, then a recipe preview | Both
3.1.4 | Review the preview: check title, ingredients, steps, tips | Recipe looks sensible and matches what was narrated | Both
3.1.5 | Check ingredient quantities: tbsp/tsp/g/oz are abbreviated, not spelled out | Abbreviations used (e.g. "1 tbsp", not "1 tablespoon") | Both
3.1.6 | Tap "Save Recipe 💾" | Redirected to the saved recipe's detail page | Both
3.1.7 | Navigate back to the library | New recipe appears in the list | Both
3.2 Paste
# | Action | Expected Result | Platform | Result | Notes
3.2.1 | Open Capture → "Paste" tab | Text area appears | Both
3.2.2 | Paste a recipe from a website or document | Text appears in the field | Both
3.2.3 | Tap "Generate Recipe" | Recipe preview generated correctly | Both
3.2.4 | Edit the recipe title before saving | Title updates | Both
3.2.5 | Save the recipe | Saved successfully | Both
3.3 URL Import
# | Action | Expected Result | Platform | Result | Notes
3.3.1 | Open Capture → "URL" tab | URL input field + Paste button appears | Both
3.3.2 | Type or paste a public recipe URL (e.g. a BBC Food recipe) | URL appears in the field | Both
3.3.3 | Tap "Import Recipe" | Fetching animation, then recipe preview | Both
3.3.4 | Check that the recipe matches the source page | Title, ingredients and steps are accurate | Both
3.3.5 | Try a URL behind a login (e.g. a paywalled site) | Friendly error message, no crash | Both
3.3.6 | Try a non-recipe URL (e.g. https://www.bbc.co.uk) | Error message or graceful fallback | Both
3.4 Photo
# | Action | Expected Result | Platform | Result | Notes
3.4.1 | Open Capture → "Photo" tab | Photo upload area appears | Both
3.4.2 | [iOS] Tap to take a photo of a recipe card or cookbook page | Photo thumbnail appears | iOS
3.4.3 | [Web] Upload a photo of a recipe from your device | Photo thumbnail appears | Web
3.4.4 | Tap "Read Photo" | Loading screen, then recipe preview | Both
3.4.5 | Add a second photo (e.g. second page of the recipe) | Both thumbnails visible; up to 5 photos can be added | Both
3.4.6 | Check the generated recipe matches the photo content | Accurate extraction | Both
3.5 Edge Cases
# | Action | Expected Result | Platform | Result | Notes
3.5.1 | Try to generate with an empty paste field | "Generate Recipe" button is disabled / greyed out | Both
3.5.2 | Start narrating, close app mid-narration, re-open | Banner offers to restore the unsaved narration | iOS
3.5.3 | Generate a recipe, then tap "← Recipe Library" without saving | "You have unsaved changes — are you sure?" prompt appears | Both
3.5.4 | Tap "Try Again" on the preview screen | Returns to capture mode, previous input cleared | Both

## 4 · Recipe Detail
4 · Recipe Detail
4.1 Viewing
# | Action | Expected Result | Platform | Result | Notes
4.1.1 | Open any saved recipe | Full recipe shown: description, category, dietary tags, allergens, servings, times, ingredients, steps, tips | Both
4.1.2 | Tap "← Recipe Library" | Returns to the library | Both
4.1.3 | Check dietary tags (e.g. for a vegan recipe) | Correct tags shown as badges | Both
4.1.4 | Check allergen labels (e.g. for a recipe with dairy) | Correct allergens listed | Both
4.2 Editing
# | Action | Expected Result | Platform | Result | Notes
4.2.1 | Tap the edit (pencil) button on a recipe | Recipe enters edit mode | Both
4.2.2 | Change the recipe title | Title updates | Both
4.2.3 | Edit an ingredient quantity | Change saved correctly | Both
4.2.4 | Add a new step | Step appears in the list | Both
4.2.5 | Save changes | Confirmation; updated recipe shown | Both
4.3 Deleting
# | Action | Expected Result | Platform | Result | Notes
4.3.1 | Tap the delete button on a recipe | Confirmation prompt appears | Both
4.3.2 | Confirm deletion | Redirected to library; recipe gone | Both
4.4 Sous Chef Button
# | Action | Expected Result | Platform | Result | Notes
4.4.1 | [Free user] Tap "Cook with Sous Chef" | Paywall screen appears (not the cooking session) | Both
4.4.2 | [Free user] Tap "← Back to Recipe" on the paywall | Returns to recipe detail | Both
4.4.3 | [Paid user] Tap "Cook with Sous Chef" | Sous Chef waiting screen appears | Both

## 5 · Sous Chef
5 · Sous Chef
5.1 Starting a Session — Paid users only (ask developer for test account if needed)
# | Action | Expected Result | Platform | Result | Notes
5.1.1 | Open Sous Chef for any recipe | Waiting screen shows recipe name and "Start Cooking" button | Both
5.1.2 | Check the back button label | Shows "← Back to Recipe" | Both
5.1.3 | Tap "Start Cooking" | Session begins; Sous Chef greets you and reads the first message aloud | Both
5.1.4 | Check that speech plays automatically | Voice reads the welcome message | Both
5.2 Voice and Conversation
# | Action | Expected Result | Platform | Result | Notes
5.2.1 | Ask a question by tapping the mic | Speech transcribed; Sous Chef responds with relevant advice | Both
5.2.2 | Ask "What's the next step?" | Sous Chef reads the next instruction aloud | Both
5.2.3 | Ask "What are the ingredients?" | Sous Chef lists them | Both
5.2.4 | Ask a follow-up question (e.g. "How long should I stir?") | Contextually relevant answer | Both
5.2.5 | [iOS] Use the volume buttons during speech | Volume changes (not the ringer) | iOS
5.2.6 | [iOS] Put the phone down; does speech continue? | Speech plays through the speaker even with screen off | iOS
5.3 Exiting
# | Action | Expected Result | Platform | Result | Notes
5.3.1 | Tap "← Back to Recipe" during a session | Returns to the recipe detail page | Both

## 6 · iOS Share Extension
6 · iOS Share Extension
iPhone only — tests saving recipes from Safari directly into Dodol
# | Action | Expected Result | Platform | Result | Notes
6.1 | Open a recipe page in Safari | Page loads | iOS
6.2 | Tap the iOS Share button (box with arrow icon) | Share sheet appears | iOS
6.3 | Find and tap "Dodol" in the share sheet | Dodol share extension opens showing the URL | iOS
6.4 | Tap "Copy Link & Open Dodol" | "Link copied" confirmation appears in the share sheet | iOS
6.5 | Open the Dodol app | App opens | iOS
6.6 | Navigate to Capture → URL tab | Paste button is visible | iOS
6.7 | Tap the "Paste" button | The recipe URL populates the input field | iOS
6.8 | Tap "Import Recipe" | Recipe is successfully imported | iOS

## 7 · Account Page
7 · Account Page
# | Action | Expected Result | Platform | Result | Notes
7.1 | Open Account page | Shows your name, email, member since date | Both
7.2 | Check navigation header | "← Recipe Library" on the left, "Account" title on the right | Both
7.3 | Tap the edit (✏️) button next to your name | Name input field appears | Both
7.4 | Change your name and save | Name updates; "Name updated ✓" confirmation shown | Both
7.5 | [Free user] Check subscription section | Shows "Free Plan" badge and recipe usage bar (e.g. "2 / 3") | Both
7.6 | [Free user] Tap "Upgrade to Pro" | Paywall / pricing screen opens | Both
7.7 | [Paid user] Check subscription section | Shows "Pro — Monthly" or "Pro — Annual" badge with renewal date | Both
7.8 | [Paid user] Tap "Manage subscription" | Stripe billing portal opens | Both

## 8 · Paywall & Subscription
8 · Paywall & Subscription
# | Action | Expected Result | Platform | Result | Notes
8.1 | [Free user] Save 3 recipes | All 3 save successfully | Both
8.2 | [Free user] Try to save a 4th recipe | Paywall modal appears | Both
8.3 | Close the paywall modal | Returned to capture; recipe not saved | Both
8.4 | On the paywall, view the plan options | Monthly and annual pricing both shown | Both
8.5 | [Optional — real payment] Select a plan and complete checkout | Redirected back to app with "Welcome to Dodol Pro" banner | Both
8.6 | After upgrading, save a 4th recipe | Saves successfully with no paywall | Both

## 9 · Navigation
9 · Navigation Consistency
Run through these quickly to verify labels are consistent across all pages.
# | Page | Back Button Text | Header Title | Result | Notes
9.1 | Recipe Detail | ← Recipe Library | (none)
9.2 | Capture a Recipe | ← Recipe Library | Capture a Recipe
9.3 | Account | ← Recipe Library | Account
9.4 | Sous Chef — waiting | ← Back to Recipe | (none / recipe name)
9.5 | Sous Chef — cooking | ← Back to Recipe | (session header)
9.6 | Sous Chef — paywall (free user) | ← Back to Recipe | (none)

## 10 · Performance
10 · Performance
# | Action | Expected Result | Platform | Result | Notes
10.1 | [iOS] Background the app mid-capture and return | State preserved | iOS
10.2 | Import a recipe from a slow or complex URL | Loading indicator shown; succeeds or shows a friendly timeout message — no crash | Both
10.3 | Try narrating for 2+ minutes continuously | Transcription continues; no crash | Both
10.4 | Have a 10+ message Sous Chef conversation | Session remains responsive throughout | Both
10.5 | Kill and relaunch the app | Returns to library; no data loss | iOS

## 11 · Error States
11 · Error States
# | Action | Expected Result | Platform | Result | Notes
11.1 | Turn on Airplane Mode and try to import a URL | Friendly "Network error" message, no crash | Both
11.2 | Turn on Airplane Mode and try to save a recipe | Friendly error message | Both
11.3 | Navigate to /recipe/fake-id | "Recipe not found" screen with back button | Both

## Feedback Summary
Feedback Summary
Please complete this after finishing all test sections. Your feedback helps improve the app.
Overall Impression
Rating (1 = Poor, 5 = Excellent)
Top 3 Things That Worked Well
1.
2.
3.
Top 3 Things That Felt Confusing or Broken
1.
2.
3.
Additional Comments
Tester Information (optional)
Name
Device / Platform tested on
Date tested